## Sheet1
Sequence of Events
GOVERNMENT (Note: This may vary widely depending on the client's purchasing process.)
Week Of | √ | Proposed Event | Billable | Responsible
|  | Gain consensus on goal and capabilities |  | Both
|  | Survey current system |  | Reseller
|  | Gain preliminary financial/budgetary approval |  | Client
|  | Write RFP with the client |  | Both
|  | Issue RFP if required |  | Client
|  | Develop implementation plan with IT |  | Reseller
|  | Share survey results and provide cost estimate |  | Reseller
|  | Develop cost vs. benefit analysis (ROI Tool) |  | Both
|  | Define success metrics |  | Both
|  | Provide documentation for Purchasing/Procurement |  | Reseller
|  | Provide contracts for legal review |  | Reseller
|  | Conduct pre-decision review |  | Reseller
|  | Deliver proposal |  | Reseller
|  | Award contract |  | Client
|  | Begin implementation |  | Both
√ Represents steps where both parties agree to continue with the sequence of events.